## User Feedback
Date | Site | User/Team | Feedback Type | Pain Point / Request | Priority | Status
1/15/24 | Nevada | Construction PM Team | Pain Point | Can't easily see which areas/systems are over budget | High
1/18/24 | GF Nevada | Project Controls | Feature Request | Want automated alerts when scope changes impact milestones | Medium | Backlog
1/22/24 | Nevada | Cost Engineer | Pain Point | Change management workflow is unclear — takes 10+ clicks to adjust scope hours | high
01/25/24 | GF Nevada | Scheduling Team | Pain Point | Milestone dates don't sync with Primavera — have to manually update both systems | High | Addressed
1/28/24 | Nevada | Vendor: MEP Contractor | Pain Point | Can't view our assigned scopes of work — permission issues | High
1/29/24 | GF Nevada | Area Manager | Feature Request | Request dashboards showing area/system progress by zone | Low | Won't Do
2/3/24 | GF Nevada | Finance Team | Pain Point | Budget rollups from tasks to scopes to areas/systems sometimes don't add up correctly | Medium
2/6/24 | Nevada | External: Design Partner | Pain Point | No way to submit scope quantity updates — have to email spreadsheets | Medium | Backlog
2/8/24 | GF Nevada | Field Supervisor | Pain Point | Tekton field data not syncing to Athena tasks — showing old hours | High
3/8/24 | Shanghai | Estimating Team | Pain Point | Bulk import of task hours fails intermittently — have to re-enter manually | High
3/12/24 | GF Shanghai | Project Manager | Feature Request | Need to track change orders separately from baseline scope | High | Prototyped
03/15/24 | Shanghai | Construction Super | Pain Point | Can't see which tasks are behind schedule without exporting to Excel | Medium | Addressed
3/18/24 | GF Shanghai | External: Structural Eng | Feature Request | Need API access to push updated quantities from our design tool | High
3/20/24 | GF Shanghai | Cost Analyst | Pain Point | Historical change management reports take 5+ min to generate |  | In Progress
3/22/24 | Shanghai | Field Coordinator | Pain Point | Tekton mobile app crashes when trying to submit hours for 50+ tasks | Medium
3/24/24 | GF Shanghai | Scheduling | Feature Request | Want Slack notifications when milestones get pushed | Low | Backlog
4/20/24 | Berlin | Procurement Team | Pain Point | Scope of work descriptions don't match our RFP format — have to rewrite | High
4/22/24 | GF Berlin | External: GC Partner | Pain Point | Athena doesn't meet our audit requirements for change tracking | High
4/25/24 | Berlin | Project Controls | Pain Point | Had cost overrun because area/system budget changes weren't flagged | high
04/28/24 | Berlin | Field Engineer | Feature Request | Request Tekton integration with photo uploads — need to link pics to tasks | Medium | Backlog
5/5/24 | GF Berlin | Finance | Pain Point | Athena broke our monthly budget variance reports — formulas incompatible | High | Addressed
5/10/24 | GF Berlin | Scheduling Lead | Pain Point | Milestone dependencies aren't visual — can't tell critical path | Medium
5/12/24 | Berlin | Foreman | Pain Point | Tekton requires too many clicks to report daily hours — slows down crew | High
5/15/24 | GF Berlin | Site Manager | Feature Request | Want to trigger scope approvals from Athena instead of email | Low | Won't Do
5/18/24 | Berlin | Vendor: Electrical Sub | Pain Point | Our task updates from Tekton don't flow back to scope totals in real-time | Medium
6/24/24 | Texas | Estimator | Pain Point | Importing estimate data loses decimal precision on hours | High
06/28/24 | GF Texas | Cost Manager | Pain Point | No way to compare actual vs. baseline after multiple change orders | Medium | Backlog
7/3/24 | Texas | Construction PM | Feature Request | Need multi-site rollup view — managing 3 buildings in Athena separately |  | In Progress
7/5/24 | GF Texas | Field Ops Lead | Pain Point | Tekton offline mode doesn't work — lose all data when jobsite has no signal | High
7/8/24 | GF Texas | External: Commissioning | Pain Point | Need read-only access to milestone status — current permissions too broad | High
7/10/24 | Texas | Project Controls | Feature Request | Change approval workflow takes too long — need 1-click approvals for small changes | High | Prototyped
7/15/24 | GF Texas | QA/QC Team | Pain Point | Can't link inspection records to tasks — manual cross-reference | High
8/10/24 | Mexico | Field Coordinator | Pain Point | Athena requires training we don't have time for — too complex | Medium
08/15/24 | GF Mexico | Finance Analyst | Feature Request | Want cost forecasting based on current burn rate | Low | Backlog
8/18/24 | Mexico | Vendor: Concrete Supplier | Pain Point | Your scope quantity update broke our material order — 6hr delay | High | Addressed
8/20/24 | Mexico | Project Manager | Pain Point | Scope change didn't trigger milestone update — had to manual fix | High | Addressed
8/22/24 | GF Mexico | Superintendent | Pain Point | Tekton doesn't show which tasks need hours today — have to check Athena separately | Medium
8/25/24 | GF Mexico | Scheduler | Pain Point | Error messages unclear — 'invalid area/system ID' doesn't say which one | medium

## Deployment Event Log
Site | Date | Event Type | Description | Days Impact | Cost Impact ($)
GF Nevada | 01/08/2024 | Kickoff | Athena deployment start; project controls team on-site | 0 | 0
Nevada | 1/12/24 | blocker | Area/system budget import failed — data format mismatch | 4 days | $35,000
GF Nevada | 2024-01-16 | Blocker | Legacy Primavera schedule integration incompatible with Athena milestones | 5 | 58000
GF Nevada | 01/20/24 | Incident | Budget rollup calculation error — showed negative costs for 3 areas/systems | 1 | 12000
Nevada | 1/28/24 | Blocker | External contractor (MEP) permissions blocked — can't access assigned scopes | 3 | 22k
GF Nevada | 2024-02-05 | Issue | Tekton field app not syncing hours to Athena — 2-day data delay | 2 | 15000
GF Nevada | Jan 23 2024 | ISSUE | Finance team requested custom cost variance reports not in scope | 2 | 18k
GF Nevada | 2024-02-10 | Closure | Athena live — 5 weeks total
Shanghai | 3/4/2024 | Kickoff | Athena deployment start | 0
GF Shanghai | 03/08/24 | issue | Task hour bulk import timing out — 500+ tasks | 1.5 | 8200
GF Shanghai | 2024-03-12 | Blocker | China data residency audit required — 3 day hold on scope data | 3 days | 22000
Shanghai | 3/18/24 | Incident | Change order workflow broke baseline tracking — external partners lost visibility 4 hrs | 0.5 | 45000
GF Shanghai | 3/22/24 | Issue | Tekton mobile app crashes on bulk task submission — field crews frustrated | 1 | 12000
GF Shanghai | 03/28/2024 | Closure | Athena live — 3.5 weeks total
Berlin | 04/15/2024 | Kickoff | Athena deployment start | 0 | 0
GF Berlin | 4/18/24 | Blocker | GDPR compliance audit flagged change management audit logs | 4 | $28,000.00
Berlin | 4/22/24 | Blocker | GC partner audit requirement — change tracking doesn't meet their SOW | 5 | 38000
GF Berlin | 2024-04-25 | incident | Monthly budget variance report integration crashed — Finance blocked 6 hrs | 1 | 15000
GF Berlin | 05/02/24 | Blocker | SAP integration conflict with area/system budget codes | 5 | 62000
GF Berlin | 2024-05-08 | Issue | Security team wants role-based access for scope changes — not configured | 3 | 31000
Berlin | 5/12/24 | Issue | Tekton offline mode data loss — field crews lost 8 hrs of entries | 1 | 18000
GF Berlin | 5/30/2024 | Closure | Athena live — 6.5 weeks total
Texas | 06/20/24 | Kickoff | Athena deployment start |  | 0
GF Texas | 2024-06-24 | incident | Estimate import lost decimal precision — all task hours rounded | 2 | 16000
GF Texas | 06/30/2024 | Blocker | Lead project controls engineer out sick for 4 days | 4 days | 28000
Texas | 7/5/24 | Blocker | Tekton offline mode not working — jobsite has poor cell coverage | 2 | 22000
Texas | 7/8/24 | Blocker | Commissioning partner VPN access delay — read-only milestone view blocked | 3 | 25000
GF Texas | 7/8/24 | Issue | Project teams want custom approval workflows for small changes — approved as add-on | 1.5 | $19k
GF Texas | 2024-07-26 | Closure | Athena live — 5 weeks total
Mexico | 8/5/2024 | Kickoff | Athena deployment start | 0 | 0
GF Mexico | 08/10/24 | Issue | Milestone date sync issue — Primavera updates not flowing to Athena | 0.5 | 6000
GF Mexico | 2024-08-15 | Blocker | Scope change approval workflow — took 8 hrs to get sign-off | 2 | 24000
Mexico | 8/18/24 | Incident | Concrete supplier material order broke after scope quantity update — 6hr delay | 1 | 52000
GF Mexico | 8/22/24 | Issue | Tekton not showing today's required task list — crews checking Athena manually | 1 | 8000
GF Mexico | 08/22/2024 | Issue | 2 project teams didn't complete Athena training before go-live | 1.5 | 9000
GF Mexico | 9/2/24 | Closure | Athena live — 4 weeks total

## Financial Records
Site | Category | Budgeted ($) | Actual ($)
Nevada | Electrical Systems | 2840000 | 3120000
GF Nevada | HVAC Systems | 4250000 | 4680000
GF Nevada | Structural Steel | 6800000 | 6950000
GF Nevada | Fire Protection | 920k | 1050000
GF Nevada | Site Work & Utilities | 1580000
GF Nevada | Concrete & Foundations | 3200000 | 3480000
GF Nevada | Targeted Savings | 850000 | 420000
Shanghai | Electrical Systems | 2640000 | 2380000
GF Shanghai | HVAC Systems | 3950000 | 3720000
GF Shanghai | Structural Steel | 6200000 | 6100000
| Fire Protection | 880000 | 825000
GF Shanghai | Site Work & Utilities | 1,420,000 | 1.38M
GF Shanghai | Concrete & Foundations | 2980000 | 2850000
GF Shanghai | Targeted Savings Used | 780000 | 0
GF Berlin | Electrical Systems | 3,180,000 | 3650000
Berlin | HVAC Systems | 4680000 | 5,240,000
GF Berlin | Structural Steel | 7400000 | 7820000
GF Berlin | Fire Protection | 1.05M | 1180000
GF Berlin | Site Work & Utilities | 1720000 | 1890000
GF Berlin | Concrete & Foundations | 3580000 | 3920000
GF Berlin | Targeted Savings Used | 920000 | 285000
Texas | Electrical Systems | 2920000 | 3.15M
GF Texas | HVAC Systems | 4180000 | 4520000
GF Texas | Structural Steel | 6650000
GF Texas | Fire Protection | 940000 | 1020000
GF Texas | Site Work & Utilities | $1,580,000 | 1640000
GF Texas | Concrete & Foundations | 3120000 | 3350000
GF Texas | Targeted Savings | 820000 | 485000
Mexico | Electrical Systems | 2,680,000 | 2920000
GF Mexico | HVAC Systems | 3880000 | 4150000
GF Mexico | Structural Steel | 6100000 | 6350000
GF Mexico | Fire Protection |  | 920000
GF Mexico | Site Work & Utilities | 1420000 | 1.52M
GF Mexico | Concrete & Foundations | 2850000 | 3080000
GF Mexico | Targeted Savings | 740000 | 420000
GF Nevada | Site Work & Utilities | 1580000 | 1720000

## Adoption Metrics
Site | Week | Areas/Systems Deployed | Users Trained | Users Blocked | Change Orders Processed | Incidents Reported
Nevada | Week 1 | 1 | 45 | 18 | 0 | 4
GF Nevada | 2 | 2 | 82 | 12 |  | 3
GF Nevada | 3 | 3 | 128 | 8 | 5 | 2
GF Nevada | 4 | 4 | 185 |  | 12 | 1
GF Nevada | 5 | 4 | 245 | 4 | 28 | 1
GF Nevada | Week 6 | 4 | 298 | 0 | 45 | 0
Shanghai | 1 | 2 | 62 | 10 | 0 | 3
GF Shanghai | Week 2 | 3 | 145 | 6 | 4 | 2
GF Shanghai | 3 | 4 | 238 | 2 | 12 orders | 1
GF Shanghai | 4 | 4 | 305 |  | 22 | 0
Berlin | Week 1 | 1 | 28 | 22 | 0 | 6
GF Berlin | 2 | 1 | 65 | 18 |  | 5
GF Berlin | 3 | 2 | 118 | 14 | 3 | 4
GF Berlin | Week 4 | 3 | 182 | 8 | 8 | 2
GF Berlin | 5 | 4 | 245 | 4 | 18 | 1
GF Berlin | 6 | 4 | 288 | 1 | 28 orders | 1
GF Berlin | 7 | 4 | 310 |  | 38 | 0
Texas | 1 | 1 | 52 | 15 | 0 | 3
GF Texas | Week 2 | 2 | 108 | 10 | 2 | 3 incidents
GF Texas | 4 | 3 | 195 | 5 | 12 | 2
GF Texas | 4 | 4 | 268 | 2 | 22 orders | 1
GF Texas | 5 | 4 | 312 | 0 | 32
Mexico | Week 1 | 2 | 85 | 8 | 0 | 2
GF Mexico | 2 | 3 | 168 | 5 | 6 | 1
GF Mexico | 3 | 4 | 245 |  | 18 | 1
GF Mexico | Week 4 | 4 | 298 | 1 | 28 | 0
GF Mexico | 5 | 4 | 315 | 0 | 35 orders | 0

## Feature Prototypes
Feature Name | Requested By | Site | Status | Implemented? | Notes
Auto-milestone update on scope change | Project Controls | Nevada | Prototyped | No | Tested in staging — broke 2 dependency chains. Needs more work.
Change order baseline tracking | Project Manager | Shanghai | Shipped | Yes | Built custom workflow. Now used by 8 teams.
Area/system progress dashboards | Area Manager | Nevada | Rejected | No | Too expensive — would require custom BI integration $12k/mo.
Slack milestone notifications | Scheduling | Shanghai | Shipped | Yes | Simple webhook integration. Took 2 days to build.
Tekton photo upload integration | Field Engineer | Berlin | Backlog | No | Requires mobile dev + storage integration. 8-week effort.
1-click change approvals | Project Controls | Texas | Prototyped | Partial | Works for cost changes < $5k. Larger changes need full workflow.
Cost forecasting dashboard | Finance Analyst | Mexico | Backlog | No | Requires ML model integration. 6-week effort + data scientist.
Multi-site rollup view | Construction PM | Texas | In Progress | Partial | Works for 2 sites. Adding cross-site reporting next sprint.
API for scope quantity updates | External: Design Partner | Nevada | Shipped | Yes | REST API with auth. Reduced manual data entry by 60%.
Improved error messages | Multiple teams | All sites | In Progress | Partial | Added context to 40% of errors. Ongoing work.
Read-only milestone access | External: Commissioning | Texas | Backlog | No | Requires role-based permissions overhaul. 4-week project.
Budget variance report fix | Finance | Berlin | Shipped | Yes | Fixed SAP integration. Monthly reports now automated.
Tekton offline mode | Field Ops Lead | Texas | Prototyped | Partial | Works for 50 tasks. Larger batches need optimization.
Tekton daily task list | Superintendent | Mexico | Backlog | No | Requires sync logic between Athena scheduling and Tekton UI. 3-week effort.

## Technical Survey
Area | Finding | Engineer | Date
Network | Primary connectivity: 1Gbps fiber. VPN latency to HQ: ~120ms avg. No egress filtering currently in place. | J. Torres | 2024-10-02
Network | Existing VLAN segmentation adequate. Will need dedicated subnet for Athena application servers. | J. Torres | 2024-10-02
Compute | Current VM estate: 45 VMs across 3 ESXi hosts. ~60% avg utilization. Can provision 8 VMs for Athena. | M. Chen | 2024-10-03
Compute | Approved AWS account exists. Current spend: $18k/mo (EC2 + RDS). Athena projected +$12k/mo. | M. Chen | 2024-10-03
Storage | On-prem NFS: 80TB capacity, 55% used. S3 bucket provisioned for Athena backups. Versioning enabled. | M. Chen | 2024-10-03
Existing PM Tools | Primavera P6 (scheduling). 140 active project schedules. Athena must integrate milestone sync. | R. Patel | 2024-10-04
Existing PM Tools | SAP (finance/budgeting). Used for approved project budgets. Athena area/system budgets must tie to SAP codes. | R. Patel | 2024-10-04
Project Structure | 18 active areas/systems identified. Avg 45 scopes of work per area/system. Estimated 2,800 tasks total. | R. Patel | 2024-10-04
Project Data | Current budgets tracked in Excel. Estimate data in Procore. Change orders in email/PDFs. All need migration to Athena. | R. Patel | 2024-10-04
Tekton Integration | Tekton mobile app used by 85 field personnel. Daily avg: 420 task hour entries. Must sync to Athena in near real-time. | R. Patel | 2024-10-04
Tekton Integration | Jobsite cell coverage spotty in zones C/D. Tekton offline mode critical — users report 2-3 hrs offline per day. | R. Patel | 2024-10-04
External Integrations | 5 external contractors require scope access: MEP, Structural, GC, Electrical, Commissioning. | R. Patel | 2024-10-04
External Integrations | 2 design partners push quantity updates: Architect firm, Structural engineer. Need API access. | R. Patel | 2024-10-04
Security | Role-based access needed: Project Controls (full), Field (Tekton task updates), Vendors (read-only scopes). | L. Garcia | 2024-10-05
Security | Change management audit trail required for compliance. All scope/cost/hour changes must be logged. | L. Garcia | 2024-10-05
Reporting | Monthly budget variance reports required. Weekly milestone status to exec team. Ad-hoc change impact analysis. | J. Torres | 2024-10-02
Reporting | Current reports: 15 Excel templates manually updated. Athena must automate or replace. | J. Torres | 2024-10-02
Team Skills | Skill survey: 60% familiar with Primavera, 40% with SAP, 25% with project management software, 10% with APIs. | L. Garcia | 2024-10-05
Team Skills | Field crews familiar with Tekton (simple UI). Athena perceived as complex — need hands-on training focused on daily workflows. | L. Garcia | 2024-10-05

## Stakeholder Contacts
Name | Title | Team/Organization | Preferred Contact | Availability / Notes
REQUIRED MEETING | Daily Standup | All Teams | In-person @ 9am | 30 minutes daily. Attendance mandatory for FDE, project teams, and project managers.
D. Nakamura | VP, Construction | Leadership | Slack / Email | Weekly summary due Fridays. Oncall week of Sprint 3 — limited availability.
K. Abrams | Site Construction Manager | Site Leadership | In-person / Slack | Attends daily standup. Traveling Sprint 2 (Wed-Fri). Owns milestone approvals.
S. Chen | Project Manager | Construction PM Team | Slack / Email | Manages 6 areas/systems. Attends daily standup. Heavy Athena user.
M. Rivers | Project Manager | MEP Coordination | In-person / Slack | Attends standups. Coordinates MEP areas/systems. Very detail-oriented on scope changes.
R. Lopez | Project Controls Lead | Project Controls | Email / Weekly calls | Tracks all budgets, cost variance. Requires weekly Athena reports by Thursday. Power user.
A. Desai | Cost Manager | Project Controls | Slack / Meetings | Owns budget approvals. Attends standups. Concerned about Athena cost rollup accuracy.
F. Mueller | Compliance Lead | Legal/Compliance | Email / Jira | Change management audit requirements. Responds within 24 hrs. Audit Sprint 4.
J. Park | Estimator | Estimating Team | Slack | Attends standups. Imports task hours from estimates. Concerned about decimal precision loss.
T. Reyes | Cost Engineer | Cost Engineering | Slack / Pair programming | Manages scope budgets. Finds change management workflow too complex. Needs training.
M. Santos | Scheduler | Scheduling Team | Slack | Attends standups. Manages Primavera sync. Wants milestone dependencies visualized.
P. Kumar | Senior PM | Project Management | Slack / In-person | Deep Athena knowledge from prior site. Happy to help other teams. Good internal advocate.
R. Kim | Construction Super | Field Operations | Slack / Email | Attends standups. Uses Tekton daily. Wants mobile app for task updates from jobsite.
B. Johnson | Field Coordinator | Field Operations | Slack | Junior role. Comfortable with Tekton. Finds Athena too complex for office work.
L. Zhang | Finance Analyst | Finance | Slack | Attends standups. Owns budget variance reports. Concerned about SAP integration.
T. Okafor | Procurement Lead | Procurement | Slack | Budget-conscious. Rejected BI dashboard due to cost. Open to built-in reports.
C. Martinez | IT Admin | Site IT | Slack / In-person | Manages on-prem servers. Concerned about Athena + Tekton sync resource requirements.
D. Lee | Data Analyst | Project Controls | PagerDuty / Slack | Builds custom reports. Needs API documentation for Athena data export.
W. Garcia | Foreman | Field Crew Lead | Tekton / In-person | Uses Tekton exclusively. Doesn't access Athena. Wants simpler Tekton daily task view.
V. Patel | Project Manager | MEP Contractor (External) | Email | Scope access issues. Needs read/write for assigned MEP scopes. 2-week notice for changes.
C. Williams | Principal | Architect Firm (External) | Email / Zoom | Pushes quantity updates from Revit. Requesting API access. SOW in progress.
H. Kim | Structural PM | Structural Engineer (Ext) | Slack (shared channel) | API integration critical. Manual quantity updates caused 4hr rework in Shanghai.
N. Rodriguez | Commissioning Mgr | Commissioning Partner (Ext) | Email | Needs read-only milestone access. Change requests go through procurement (slow).
E. Johnson | GC Project Manager | General Contractor (Vendor) | Email / Phone | Audit requirements for change tracking. Athena must meet their documentation standards.